## PRODUCT BACKLOG
PRODUCT BACKLOG
ID | Feature | Category | Priority | Sprint 1 | Todo | Done? | Sprint 2 | Todo | Done | Sprint 3 | Todo | Done
0 | Display menu screen on program start | Menu | M | x | nee | Ja
1 | Menu with "start game" and "exit" buttons | Menu | M | x | nee | Ja
2 | Show the rules of the game when needed by user | Menu or Turn | M |  |  |  | x | nee | ja
3 | Screen to name players | Menu | C
4 | Display game board | Init | M |  |  |  | x | nee | ja
5 | Place the boats on the starting positions | Init | M | [6 empty] | x | nee | ja
6 | Display "exit" button | Init and Turn | M |  |  |  | x | nee | ja
7 | Display which player is playing the current turn | Turn | M | [6 empty] | x | nee | ja
9 | Let the player move their boats in the amount of steps they are allowed to take | Turn | M | [6 empty] | x | nee | ja
10 | Execute special actions when cards are activated | Turn | M | [6 empty] | x | nee | ja
11 | Change current player after the end of the turn | Turn | M | [6 empty] | x | nee | ja
12 | Show win screen if all enemy boats are destroyed | End | M | [6 empty] | x | nee | ja
13 | "Go back to menu" button is displayed in the win screen | End | S | [6 empty] | x | nee | ja
14 | Current player can pause and resume the game | Turn | S
15 | Produce sound for Moving boats, winning, special moves | Turn | C
16 | Display animation for moving boats | Turn | C
17 | Menu extended with "settings" button | Menu | C |  |  |  | x | nee | ja
18 | Possibility to select also computer players | Init | C
19 | Computer player is able to play the game | Turn | C
20 | Add some humour to the computer player | Turn | W
21 | Save current state of the game on a file | Turn | C
22 | Load a previously saved game state | Menu | C
23 | Make game playable online | Browser | C
24 | Make game playable by users sitting at different PCs (LAN multiplayer) | Menu and Turn | C
25 | Instructions show on first start up | Menu | C
26 | Create a github folder | None | M | x | nee | Ja
27 | Create a card list | None | M |  |  |  | x | nee | ja
28 | Create Highscore | Menu | S |  |  |  | x | nee | ja

## SPRINT 1 BACKLOG
SPRINT 1 BACKLOG
ID | User story | Priority | Time Estimation | Tasks | Acceptance criteria
0 | As an user I want to see a menu when I start the game, so I can start a new game or exit the game | M | 12 | - Create a "Start game" button - Create a "Exit" button | - The exit Button works - Start button shows
1 | As an user I want a menu with buttons, so I can start and exit the game | M | 5 | - Create 2 buttons - Place buttons on right position | - 2 Buttons - The buttons on the right positions
26 | Create a github folder | M | 1 | - Create a folder structure - Give everybody rights to push & pull | - A proper folder structure - Everybody in our group has excess to the git
|  | total points | 18

## SPRINT 2 BACKLOG
SPRINT 2 BACKLOG
ID | User story | Priority | Time Estimation | Tasks | Acceptance criteria
2 | As an user I want to be able to look at the rules at any time, so I know what I'm supposed to do | M | 8 | - make a tab with all the rules - Make a button in menu named "Rules" | - The rulebook is shown - The rulebook is readeble for the user - users can access the rules in game and in the menu
4 | As an user I want a playing field, so I am able to play the game | M | 40 | - Design a playing field - Implement playing field in code | - A proper playing field - playing field is shown when pressing "start game" - Playing field goes away when pressing "Exit button"
6 | As an user I want to be able to quit the game at any time when I am playing the game, so I can go do something else | M | 5 | - Place the Quit button on the playing field - let the Quit button go back to the menu | - Quit button goes to the menu - Quit button is visible for the user
17 | As an User I want a settings tab, so I can turn off the music | C | 8 | - Create a settings button in the menu - Create an option to shut down music - Create a "Back" button to go back to the menu | - Settings button in Menu - Option to turn on/off music
27 | As an user I want to have a card deck, so I can use cards in my turn when I am playing the game | M | 20 | - Create a card list in a database or list - Give a value to the cards | - Cardlist in the database
28 | As an user I want to see the best scores, So I can know what I have to beat | S | 13 | - Create a database - Create database connection - Get a list with Highscores | - A list of highscores
|  | total points | 94

## Sprint 3 backlog
SPRINT 3 BACKLOG
ID | User story | Priority | Time Estimation | Tasks | Acceptance criteria
5 | As an user I want the boats to be in a certain position, so the boats do not spawn random next to each other | M | 20 | - Create boats - Give boats a position | - Boats are visible on the screen - Boats have a position on the screen - Player1 boats are green colored - Player2 boats are red colored
7 | As an user I want to see who´s turn it is, so its clear if player 1 or 2 can move the boats | M | 8 | - Make a text box with the name of the player who´s turn it is | - Display a tekst box with the playername who's turn it is
9 | As an user I want to be able to move the boats, So I can get in range to shoot at my opponent | M | 13 | - Create a movement Method - Create a Turn to defence method | - The boats can move a certain steps - The boat can be forced into defence mode
10 | As an User I want to be able to activate cards, so I can power up my boats | M | 13 | - Let a user draw cards - Let the user activate cards - Let the user select a boat to activate the card on | - the player can activate cards - The player can draw cards - the player can set cards face down on the field
11 | As an user I want to be able to end my turn, so my opponent can make his move | M | 5 | - Create a endturn button - give the endturn button a value to let the other player make his turn | - The end turn button end the players turn - Resets the movement values so the boats can move next turn
12 | As an user I want to know when I win the game, so I know when the game is finished | M | 3 | - Create a win screen | - If the player wins their will be a pop up with a win screen
13 | "Go back to menu" button is displayed in the win screen | S | 1 | - Create a back to menu button in the win screen | - The button goes back to the menu
|  | total points | 63